## Graph
Project Portfolio Results
Number | Project | Impact Score | Effort Score
1 | iPad Lab Pilot | 5.8182 | 1.7143
2 | DA Flea Market | 4.3636 | 1.2143
3 | CalPERS Benefits Transition Project | 5.6364 | 4.3571
4 | Banner implementation -BDMS for purchasing | 5.5455 | 5.1429
5 | #REF! | #REF! | #REF!
6 | #REF! | #REF! | #REF!
7 | #REF! | #REF! | #REF!
8 | #REF! | #REF! | #REF!
9 | #REF! | #REF! | #REF!
10 | #REF! | #REF! | #REF!
11 | #REF! | #REF! | #REF!
12 | #REF! | #REF! | #REF!
13 | #REF! | #REF! | #REF!

## All Projects
# | Title | Description | ETS Lead | User Lead | Supports | Enhancement
1 | iPad Lab Pilot | As a result of the last Foothill Technology meeting and Fred Sherman’s recommendation; PSME will like to request access to the district wireless network to be able to connect iPad devices to Apple TVs located in buildings 4200 and 4300. Currently the iPads and one of the AppleTVs are connecting to the “Foothill Lab” wireless network but the Airplay feature, which allow the ipads to send their video signal using the wireless network to the AppleTV device connected to the video projector is not working. I do not know if this is due to some network ports being blocked by the network. We briefly tried using a local wireless access point and the connection was successful. This is what we would like to accomplish. We would like to have tablets (iPads or android tablets) and the Apple TV devices connect to the “Foothill Lab” wireless network. This will allow the iPads access our local VMware servers (VDI) and also send video signal using Airplay to the apple TV devices. Please support the Proof of concept to see if this kind of setup would be reasonable and adequate for our classrooms and faculty use. | Sharon Luciw | Peter Murray | Affect Workforce Development, Basic Skills, and Transfer | Will significantly enhance business, student, or instructional services
2 | DA Flea Market | We've been without a dedicated phone line and network connection out in the parking lots where the Flea Market is held for decades and can continue without them until this work can be completed (for now we can continue to use our cell phones for voice as we have been). Please note that the Flea Market Office in the Campus Center in Room HCC 158 has had phone (x8414) and data forever. While emergency phones in the parking lots would be good and should be added we would still like a phone in the Flea Market Information Booth for emergency and other uses. We already have a phone and extension we want to use there, x8350. the main file we need to access on our file server is an Access database containing all our vendor data. Security is an issue because the vendor data includes names, addresses, Driver's License Numbers, and even Social Security Numbers in some cases. In addition to the uses I had mentioned earlier I was reminded of another reason we want a network connection there and that is so that the Student Employees for the Flea Market can enter their time-sheets in MyPortal while they are there. I just had to call six out of the ten students we had at the January Flea Market to remind them to submit their hours. Funding available and must be used by 6/30/12. | Sharon Luciw | Dennis Shannakian | Create efficiencies and reduce costs. Funds from this program contribute to educational programs. | Will moderately enhance business, student, or instructional services
3 | CalPERS Benefits Transition Project | We are transitioning from self funded to fully insured program provided by CalPers effective July 1, 2012. We are going to pay monthly premium for headcounts we have to Calpers, we no longer bear the liability that exceeding the monthly budgeted expenses. From system point of view, we are going from 3 to 6 medical programs, there will be more supporting needs from ETS, we are still going to use SECOVA for program intake. We will use Banner more to handle the program. | Chien Shih | Chris Vo | Strategically align to collect early withdraw of fundings from employee groups | Is critical for infrastructure improvement
4 | Banner implementation -BDMS for purchasing | This project will automate the documentation supporting of the purchasing process, project scope will include the scanning of the support documents (quote, contract, correspondence, amendament..etc) into Banner Document Management System (BDMS). Once the document is scanned into the system, it will be linked into the main Banner system and can be pulled up for review anywhere, anytime. It becomes a permanent electronic record associated with the purchasing process. | Chien Shih | Carmen Redmond | Efficiency and better collaboration among different college departments and central services. | Will significantly enhance business, student, or instructional services
5 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
6 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
8 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
9 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
10 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
11 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
12 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
13 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!

## iPad Lab
Section 1: General Project Information
Project Title: | iPad Lab Pilot
Project Description: | As a result of the last Foothill Technology meeting and Fred Sherman’s recommendation; PSME will like to request access to the district wireless network to be able to connect iPad devices to Apple TVs located in buildings 4200 and 4300. Currently the iPads and one of the AppleTVs are connecting to the “Foothill Lab” wireless network but the Airplay feature, which allow the ipads to send their video signal using the wireless network to the AppleTV device connected to the video projector is not working. I do not know if this is due to some network ports being blocked by the network. We briefly tried using a local wireless access point and the connection was successful. This is what we would like to accomplish. We would like to have tablets (iPads or android tablets) and the Apple TV devices connect to the “Foothill Lab” wireless network. This will allow the iPads access our local VMware servers (VDI) and also send video signal using Airplay to the apple TV devices. Please support the Proof of concept to see if this kind of setup would be reasonable and adequate for our classrooms and faculty use.
Project Category: | Instructional system enhancement | Date Form Submitted: | 2012-02-10
Functional Representative Filling Out Form: | Peter Murray | Has project been discussed with IT? | Yes
IT Representative Filling Out form: | Sharon Luciw | Requested Completion Date: | Pilot
User Project Lead: | Peter Murray | Has funding already been identified? | Yes
Section 2: Project Objectives and Criticality (affects Impact axis)
Relationship to Strategic Plan Elements (Goals, Commitments, Objectives & SLOs) | Supports / Enhances Achievement of a few | List All Applicable Strategic Planning Goals, Commitmments, Objectives and SLOs that this Project will Address
Enhancement | Will significantly enhance business, student, or instructional services | Affect Workforce Development, Basic Skills, and Transfer
Sponsor's Priority | High
Section 3: Project Benefits (affects Impact axis)
Students Who Could Benefit (directly) | Affects All students at one college | Financial Impact (annual net income increase): | Increase is < $5k
Employees Who Could Benefit (directly) | Affects Many Employees >50 | Time Savings | Saves < 10 hrs per week
Expected Client Satisfaction | High increase | Probability of Realizing Benefits | High Probability
Unique or duplicated services | Will replace all existing systems which have similar functionality
Section 4: Project Effort (affects Effort axis)
Departments Involved in Implemenation (exclude ETS) | Multiple Functional Departments / Academic Divisions at one college | Name the Participating Departments:
Business Process Changes Required | A few business processes will need to change as a result | Foothill PSME, ETS
Additional Ongoing Support Required (functional departments) | Less than .25 FTE
Additional Ongoing Support Required (IT) | Less than .25 FTE
Implementation Hard Costs (one time) | Cost is < $5k
Additional Ongoing Hard Costs (annual) | Cost is < $5k
Time to Implement (includes all IT and functional department work) | Time is between 1 week and 2 weeks total
Complexity of Implementation: | Some vendor interfaces, multiple system relationships, multiple dependencies
Hardware / Application Hosting by Vendor | Not applicable
Section 5: Final Prioritization Score | (for: iPad Lab Pilot)
Calculated Impact Score | 5.8182 | Automatically calculated after sections 2-4 above are completed.
Calculated Effort Score | 1.7143

## DA Flea
Section 1: General Project Information
Project Title: | DA Flea Market
Project Description: | We've been without a dedicated phone line and network connection out in the parking lots where the Flea Market is held for decades and can continue without them until this work can be completed (for now we can continue to use our cell phones for voice as we have been). Please note that the Flea Market Office in the Campus Center in Room HCC 158 has had phone (x8414) and data forever. While emergency phones in the parking lots would be good and should be added we would still like a phone in the Flea Market Information Booth for emergency and other uses. We already have a phone and extension we want to use there, x8350. the main file we need to access on our file server is an Access database containing all our vendor data. Security is an issue because the vendor data includes names, addresses, Driver's License Numbers, and even Social Security Numbers in some cases. In addition to the uses I had mentioned earlier I was reminded of another reason we want a network connection there and that is so that the Student Employees for the Flea Market can enter their time-sheets in MyPortal while they are there. I just had to call six out of the ten students we had at the January Flea Market to remind them to submit their hours. Funding available and must be used by 6/30/12.
Project Category: | IT infrastructure enhancement | Date Form Submitted: | 2012-02-13
Functional Representative Filling Out Form: | John Cognetta | Has project been discussed with IT? | Yes
IT Representative Filling Out form: | Sharon Luciw | Requested Completion Date: | 2012-05-31
User Project Lead: | Dennis Shannakian | Has funding already been identified? | Yes
Section 2: Project Objectives and Criticality (affects Impact axis)
Relationship to Strategic Plan Elements (Goals, Commitments, Objectives & SLOs) | Supports / Enhances Achievement of a few | List All Applicable Strategic Planning Goals, Commitmments, Objectives and SLOs that this Project will Address
Enhancement | Will moderately enhance business, student, or instructional services | Create efficiencies and reduce costs. Funds from this program contribute to educational programs.
Sponsor's Priority | High
Section 3: Project Benefits (affects Impact axis)
Students Who Could Benefit (directly) | Affects All students at one college | Financial Impact (annual net income increase): | Increase is between $5k and $25k
Employees Who Could Benefit (directly) | Affects Few Employees <50 | Time Savings | Saves < 10 hrs per week
Expected Client Satisfaction | High increase | Probability of Realizing Benefits | High Probability
Unique or duplicated services | Will duplicate some functionality of an existing system(s) at either college
Section 4: Project Effort (affects Effort axis)
Departments Involved in Implemenation (exclude ETS) | Single Functional Department / Academic Division | Name the Participating Departments:
Business Process Changes Required | A few business processes will need to change as a result | De Anza Office of College Life, Plant Services, ETS
Additional Ongoing Support Required (functional departments) | Less than .25 FTE
Additional Ongoing Support Required (IT) | Less than .25 FTE
Implementation Hard Costs (one time) | Cost is between $5k and $25k
Additional Ongoing Hard Costs (annual) | Cost is < $5k
Time to Implement (includes all IT and functional department work) | Time is between 1 week and 2 weeks total
Complexity of Implementation: | Simple vendor interface, no data migration
Hardware / Application Hosting by Vendor | Not applicable
Section 5: Final Prioritization Score | (for: DA Flea Market)
Calculated Impact Score | 4.3636 | Automatically calculated after sections 2-4 above are completed.
Calculated Effort Score | 1.2143

## CalPERS
Section 1: General Project Information
Project Title: | CalPERS Benefits Transition Project
Project Description: | We are transitioning from self funded to fully insured program provided by CalPers effective July 1, 2012. We are going to pay monthly premium for headcounts we have to Calpers, we no longer bear the liability that exceeding the monthly budgeted expenses. From system point of view, we are going from 3 to 6 medical programs, there will be more supporting needs from ETS, we are still going to use SECOVA for program intake. We will use Banner more to handle the program.
Project Category: | Administrative / business system enhancement | Date Form Submitted: | 2012-01-24
Functional Representative Filling Out Form: | Chris Vo | Has project been discussed with IT? | Yes
IT Representative Filling Out form: | Chien Shih | Requested Completion Date: | 2012-06-20
User Project Lead: | Chris Vo | Has funding already been identified? | Yes
Section 2: Project Objectives and Criticality (affects Impact axis)
Relationship to Strategic Plan Elements (Goals, Commitments, Objectives & SLOs) | Critical to Achievement of one or more | List All Applicable Strategic Planning Goals, Commitmments, Objectives and SLOs that this Project will Address
Enhancement | Is critical for infrastructure improvement | Strategically align to collect early withdraw of fundings from employee groups
Sponsor's Priority | High
Section 3: Project Benefits (affects Impact axis)
Students Who Could Benefit (directly) | Doesn't Affect Students | Financial Impact (annual net income increase): | Increase is > $100k
Employees Who Could Benefit (directly) | Affects All employees at district | Time Savings | Saves < 10 hrs per week
Expected Client Satisfaction | Minimal increase | Probability of Realizing Benefits | High Probability
Unique or duplicated services | Will duplicate some functionality of an existing system(s) at either college
Section 4: Project Effort (affects Effort axis)
Departments Involved in Implemenation (exclude ETS) | Multiple Functional Departments / Academic Divisions at both colleges | Name the Participating Departments:
Business Process Changes Required | Several business processes will need to change as a result | Accounting, payroll, benefits, HR, budgeting, ETS
Additional Ongoing Support Required (functional departments) | Between .50 and .75 FTE
Additional Ongoing Support Required (IT) | Between .50 and .75 FTE
Implementation Hard Costs (one time) | Cost is between $25k and $50k
Additional Ongoing Hard Costs (annual) | Cost is between $5k and $25k
Time to Implement (includes all IT and functional department work) | Time is > 6 months total
Complexity of Implementation: | Some vendor interfaces, multiple system relationships, multiple dependencies
Hardware / Application Hosting by Vendor | Not applicable
Section 5: Final Prioritization Score | (for: CalPERS Benefits Transition Project)
Calculated Impact Score | 5.6364 | Automatically calculated after sections 2-4 above are completed.
Calculated Effort Score | 4.3571

## BDMS Purchasing
Section 1: General Project Information
Project Title: | Banner implementation -BDMS for purchasing
Project Description: | This project will automate the documentation supporting of the purchasing process, project scope will include the scanning of the support documents (quote, contract, correspondence, amendament..etc) into Banner Document Management System (BDMS). Once the document is scanned into the system, it will be linked into the main Banner system and can be pulled up for review anywhere, anytime. It becomes a permanent electronic record associated with the purchasing process.
Project Category: | Administrative / business system enhancement | Date Form Submitted: | 2012-03-05
Functional Representative Filling Out Form: | Carmen Redmond | Has project been discussed with IT? | yes
IT Representative Filling Out form: | Chien Shih | Requested Completion Date: | end of 2013
User Project Lead: | Carmen Redmond | Has funding already been identified? | Yes
Section 2: Project Objectives and Criticality (affects Impact axis)
Relationship to Strategic Plan Elements (Goals, Commitments, Objectives & SLOs) | Critical to Achievement of one or more | List All Applicable Strategic Planning Goals, Commitmments, Objectives and SLOs that this Project will Address
Enhancement | Will significantly enhance business, student, or instructional services | Efficiency and better collaboration among different college departments and central services.
Sponsor's Priority | Medium
Section 3: Project Benefits (affects Impact axis)
Students Who Could Benefit (directly) | Doesn't Affect Students | Financial Impact (annual net income increase): | Increase is between $25k and $50k
Employees Who Could Benefit (directly) | Affects All employees at district | Time Savings | Saves 50 to 75 hrs per week
Expected Client Satisfaction | Moderate increase | Probability of Realizing Benefits | High Probability
Unique or duplicated services | Will replace all existing systems which have similar functionality
Section 4: Project Effort (affects Effort axis)
Departments Involved in Implemenation (exclude ETS) | Involves most departments across the district | Name the Participating Departments:
Business Process Changes Required | A few business processes will need to change as a result | Purchasing department, Controller office Measure C Accountants, Gilbane (contractor), both colleges that submited PR, Central services.
Additional Ongoing Support Required (functional departments) | Less than .25 FTE
Additional Ongoing Support Required (IT) | Between .75 and 1.0 FTE
Implementation Hard Costs (one time) | Cost is between $25k and $50k
Additional Ongoing Hard Costs (annual) | Cost is between $5k and $25k
Time to Implement (includes all IT and functional department work) | Time is > 6 months total
Complexity of Implementation: | Substantial vendor interfaces, complex system relationships, data migration
Hardware / Application Hosting by Vendor | Not applicable
Section 5: Final Prioritization Score | (for: Banner implementation -BDMS for purchasing)
Calculated Impact Score | 5.5455 | Automatically calculated after sections 2-4 above are completed.
Calculated Effort Score | 5.1429

## Drop Down 1 (hidden)
Factors | Cell Range Names
Yes/No | YN
Yes
No
Yes/No/NA
Yes | YNNA
No
N/A
Project Category | Category
Other | ScoreCategory
Student body system enhancement
Facilities system enhancement
Administrative / business system enhancement
Instructional system enhancement
IT infrastructure enhancement

## Drop Down 2 (hidden)
Factors | Score | Weight | Max Value | Percentage Impact | Cell Range Names
PROJECT IMPACT
Section 2: Project Objectives and Criticality (affects Impact axis)
Relationship to Strategic Plan Elements (Goals, Commitments, Objectives & SLOs) |  |  |  |  | StrategicAlignment
Not Aligned With Any | 0 | 1 |  |  | ScoreStrategicAlignment
Supports / Enhances Achievement of a few | 3 | 1
Supports / Enhances Achievement of several | 7 | 1
Critical to Achievement of one or more | 10 | 1 | 10 | 9.091%
Enhancement |  |  |  |  | Criticality
Will not enhance business, student, or instructional services | 0 | 2 |  |  | ScoreCriticality
Will moderately enhance business, student, or instructional services | 3 | 2
Will significantly enhance business, student, or instructional services | 6 | 2
Is critical for infrastructure improvement | 9 | 2
Is critical for Health, Life, or Safety | 10 | 2
Is necessary to comply with Regulatory / legal mandate | 10 | 2 | 20 | 18.18%
Sponsor's Priority |  |  |  |  | SponsorsPriority
Low | 0 | 1 |  |  | ScoreSponsorPriority
Medium | 5 | 1
High | 10 | 1 | 10 | 9.091%
Section 3: Project Benefits (affects Impact axis)
Students Who Could Benefit (directly) |  |  |  |  | Students
Doesn't Affect Students | 0 | 2 |  |  | ScoreStudents
Affects few Students <500 | 2 | 2
Affects Many Students >500 | 5 | 2
Affects All students at one college | 7 | 2
Affects All students at both colleges | 10 | 2
Employees Who Could Benefit (directly) |  |  |  |  | Employees
Doesn't Affect Employees | 0 | 1 |  |  | ScoreEmployees
Affects Few Employees <50 | 2 | 1
Affects Many Employees >50 | 5 | 1
Affects All employees at one college | 7 | 1
Affects All employees at district | 10 | 1
Expected Client Satisfaction |  |  |  |  | ClientSatisfaction
Minimal increase |  | 0.2 |  |  | ScoreClientSatisification
Moderate increase |  | 0.5
High increase |  | 1 | 30 | 27.27%
Financial Impact (annual net income increase): |  |  |  |  | FinancialImpact
Increase is < $5k | 0 | 1 |  |  | ScoreFinancialImpact
Increase is between $5k and $25k | 1 | 1
Increase is between $25k and $50k | 3 | 1
Increase is between $50k and $100k | 6 | 1
Increase is > $100k | 10 | 1 | 10 | 9.091%
Time Savings |  |  |  |  | TimeSavings
Saves < 10 hrs per week | 0 | 1 |  |  | ScoreTimeSavings
Saves 11 to 25 hrs per week | 1 | 1
Saves 25 to 50 hrs per week | 3 | 1
Saves 50 to 75 hrs per week | 6 | 1
Saves > 75 hrs per week | 10 | 1 | 10 | 9.091%
Probability of Realizing Benefits |  |  |  |  | Benefits
Low Probability | 0 | 1 |  |  | ScoreBenefits
Even Probability (50/50) | 3 | 1
High Probability | 10 | 1 | 10 | 9.091%
Unique or duplicated services |  |  |  |  | UniqueServices
Will duplicate most functionality of an existing system(s) at either college | 0 | 1 |  |  | ScoreUniqueServices
Will duplicate some functionality of an existing system(s) at either college | 2 | 1
Will replace all existing systems which have similar functionality | 10 | 1
Will provide unique functionality | 10 | 1 | 10 | 9.091%
| Total Points |  | 110 | 100%
PROJECT EFFORT
Section 4: Project Effort (affects Effort axis)
Departments Involved in Implemenation (exclude ETS) |  |  |  |  | Departments
Single Functional Department / Academic Division | 1 | 1 |  |  | ScoreDepartments
Multiple Functional Departments / Academic Divisions at one college | 3 | 1
Multiple Functional Departments / Academic Divisions at both colleges | 6 | 1
Involves most departments across the district | 10 | 1 | 10 | 7.143%
Business Process Changes Required |  |  |  |  | BPC
No business process will need to change as a result | 0 | 1 |  |  | ScoreBPC
A few business processes will need to change as a result | 3 | 1
Several business processes will need to change as a result | 6 | 1
Many business processes will need to change as a result | 10 | 1 | 10 | 7.143%
Additional Ongoing Support Required (functional departments) |  |  |  |  | NonIT_FTE
Less than .25 FTE | 1 | 2 |  |  | ScoreNonIT_FTE
Between .25 and .50 FTE | 2 | 2
Between .50 and .75 FTE | 3 | 2
Between .75 and 1.0 FTE | 6 | 2
More than 1.0 FTE | 10 | 2 | 20 | 14.29%
Additional Ongoing Support Required (IT) |  |  |  |  | FTE
Less than .25 FTE | 1 | 2 |  |  | ScoreIT_FTE
Between .25 and .50 FTE | 2 | 2
Between .50 and .75 FTE | 3 | 2
Between .75 and 1.0 FTE | 6 | 2
More than 1.0 FTE | 10 | 2 | 20 | 14.29%
Implementation Hard Costs (one time) |  |  |  |  | Cost
Cost is < $5k | 0 | 1 |  |  | ScoreCost
Cost is between $5k and $25k | 1 | 1
Cost is between $25k and $50k | 3 | 1
Cost is between $50k and $100k | 6 | 1
Cost is > $100k | 10 | 1 | 10 | 7.143%
Additional Ongoing Hard Costs (annual) |  |  |  |  | CostOngoing
Cost is < $5k | 0 | 2 |  |  | ScoreCostOngoing
Cost is between $5k and $25k | 1 | 2
Cost is between $25k and $50k | 3 | 2
Cost is between $50k and $100k | 6 | 2
Cost is > $100k | 10 | 2 | 20 | 14.29%
Time to Implement (includes all IT and functional department work) |  |  |  |  | Time
Time is < 1 week total | 0 | 2 |  |  | ScoreTime
Time is between 1 week and 2 weeks total | 1 | 2
Time is between 2 weeks and 1 month total | 3 | 2
Time is between 1 month and 6 months total | 6 | 2
Time is > 6 months total | 10 | 2 | 20 | 14.29%
Complexity of Implementation: |  |  |  |  | Complexity
Minimal reconfiguration of tables etc. on existing system | 1 | 2 |  |  | ScoreComplexity
Simple vendor interface, no data migration | 3 | 2
Some vendor interfaces, multiple system relationships, multiple dependencies | 6 | 2
Substantial vendor interfaces, complex system relationships, data migration | 10 | 2 | 20 | 14.29%
Hardware / Application Hosting by Vendor |  |  |  |  | Hosting
Available | 0 | 1 |  |  | ScoreHosting
Not applicable | 5
Not available | 10 | 1 | 10 | 7.143%
|  |  | 140 | 100%
0
Possible change to "Business Process Change Required"
How many are affected by significant business process change
Employees at one department in one college
Employees at multiple departments in one college
Employees in multiple departments in both colleges &/or central services
All employees across the district